## sprint-1
Agile Test Plan
Project Name |  |  | Browser:
Test Case ID |  |  | Version:
Written By: |  |  | Description:
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 |  | Enter valid username and password and click login | User is authenticated and redirected to dashboard | after verification it redirected to dashboard | Pass
2 |  | Enter invalid credentials and attempt login | Error message displayed | error message displayed | Pass
3 |  | Add a new monitoring location | Location is stored successfully | Location is stored | Pass
4 |  | Enter valid AQI value (0–500) and submit | AQI data stored in database | Stored in DB | Pass
5 |  | Enter AQI value > 500 | Validation error displayed | invalid error shown when value >500 | Pass
6 |  | Open dashboard to view AQI data | AQI records displayed correctly | AQI records are displayed | Pass
Create a Test Plan in Smartsheet

## sprint-2
Agile Test Plan
Project Name |  |  | Browser:
Test Case ID |  |  | Version:
Written By: |  |  | Description:
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Pass?
7 |  | Upload valid CSV file | Dataset processed and stored
8 |  | Upload invalid CSV format | Error message displayed
9 |  | Trigger API data fetch | AQI data retrieved and stored | Didnt fetch data | failed
10 |  | Simulate API failure | Error message displayed | error not shown
Create a Test Plan in Smartsheet

## Sheet2
FALSE
TRUE
FALSE
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE