## Sheet1
Agile Product Backlog — Air Quality Monitoring & Health Advisory System
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
SPRINT 1 |  |  | High | Complete | 24 | Yes
Implement JWT Authentication (US-01) | Yes | Yes | High | Complete | 8 | Yes
Location Management API (US-02) | Yes | Yes | High | Complete | 8 | Yes
Manual AQI Entry & Validation (US-03) | Yes | Yes | High | Complete | 8 | Yes
SPRINT 2 |  |  | High | In Progress | 56 | Yes
CSV Bulk Upload (US-05) | Yes | Yes | Medium | Complete | 13 | Yes
OpenAQ API Integration (US-06) | Yes | Yes | Medium | In Progress | 13 | Yes
AQI Trend Chart / Visualisation (US-07) | Yes | Yes | Medium | In Progress | 13 | Yes
Health Advisory Banner (US-08) | Yes | Yes | Medium | Complete | 8 | Yes
Citizen Login & Public View (US-09) | Yes | Yes | High | In Progress | 9 | Yes
SPRINT 3 |  |  | Medium | Not Started | 56 | No
Citizen Dashboard – AQI & Filter (US-10,11) | Yes | Yes | High | Not Started | 13 | No
Log Activities Model & API (US-12) | Yes | No | Medium | Not Started | 13 | No
Exposure History & Calculation (US-13,14) | Yes | No | Medium | Not Started | 16 | No
Admin – Manage Users (US-15) | Yes | No | Medium | Not Started | 8 | No
Admin – Advisory Rules & Reports (US-16,17) | Yes | No | Low | Not Started | 6 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started