## sprint-1
Agile Test Plan – Sprint 1 ¦ Air Quality Monitoring & Health Advisory System
Project Name: | Air Quality Monitoring & Health Advisory System |  | Browser: | Chrome 124 / Firefox 125
Test Case ID: | TC-S1 |  | Version: | 1.0
Written By: | Project Team |  | Description: | Sprint 1 – Officer auth, locations, manual AQI entry, dashboard
Tested By: | Project Team |  | Tested On: | 2026-03-10
Test # | Date | Action / Test Step | Expected Results | Actual Results | Pass?
1.0 | 2026-03-10 | Register as Environmental Officer with valid credentials | Account created; redirected to dashboard | Account created and redirected | Pass
2.0 | 2026-03-10 | Login with valid officer credentials | JWT tokens returned; user redirected to dashboard | Redirected to dashboard | Pass
3.0 | 2026-03-10 | Login with invalid password | Error message: 'Invalid credentials' | Error message displayed | Pass
4.0 | 2026-03-10 | Add a new monitoring location | Location saved; appears in location list | Location stored correctly | Pass
5.0 | 2026-03-10 | Enter valid AQI value (e.g. 85) and submit | AQI reading stored in database | Reading stored in DB | Pass
6.0 | 2026-03-10 | Enter AQI value > 500 (e.g. 600) | Validation error: 'AQI must be 0–500' | Error shown, data not saved | Pass
7.0 | 2026-03-10 | Enter AQI reading without selecting a location | Prompt: 'Please select a location' | Error prompt displayed | Pass
8.0 | 2026-03-10 | Open dashboard; view AQI records table | All AQI readings displayed with location & timestamp | Records displayed correctly | Pass
9.0 | 2026-03-10 | Unauthenticated user attempts to access /aqi-readings/ | 401 Unauthorized returned | 401 returned | Pass

## sprint-2
Agile Test Plan – Sprint 2 ¦ Air Quality Monitoring & Health Advisory System
Project Name: | Air Quality Monitoring & Health Advisory System |  | Browser: | Chrome 124 / Firefox 125
Test Case ID: | TC-S2 |  | Version: | 1.0
Written By: | Project Team |  | Description: | Sprint 2 – CSV upload, OpenAQ, chart, advisory, citizen login
Tested By: | Project Team |  | Tested On: | 2026-03-20
Test # | Date | Action / Test Step | Expected Results | Actual Results | Pass?
10.0 | 2026-03-20 | Upload valid CSV file (AQI_Template.csv) | All records parsed and stored; success message shown | Records stored, success shown | Pass
11.0 | 2026-03-20 | Upload CSV with AQI value > 500 | Invalid rows rejected; error log shown | Rows rejected | Pass
12.0 | 2026-03-20 | Upload CSV with missing required columns | Upload rejected: 'Invalid CSV format' | Error displayed | Pass
13.0 | 2026-03-20 | Trigger OpenAQ API fetch via POST /fetch-openaq/ | AQI data retrieved and stored | API fetch failed – error returned | Fail
14.0 | 2026-03-20 | Simulate OpenAQ API failure (invalid city) | Error message displayed; no data stored | Error not surfaced to user | Fail
15.0 | 2026-03-20 | View AQI trend chart on dashboard | Plotly line chart rendered with colour bands | Chart rendered without colour bands | Fail
16.0 | 2026-03-20 | View health advisory banner for AQI = 125 | Banner shows 'Unhealthy for Sensitive Groups' in orange | Correct banner shown | Pass
17.0 | 2026-03-20 | Register as Citizen and login | Citizen account created; AQI form hidden | AQI form hidden correctly | Pass
18.0 | 2026-03-20 | Citizen attempts POST /aqi-readings/ | 403 Forbidden returned | 403 returned | Pass

## Sheet2
FALSE
TRUE
FALSE
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## sprint-3
Agile Test Plan – Sprint 3 ¦ Air Quality Monitoring & Health Advisory System
Project Name: | Air Quality Monitoring & Health Advisory System |  | Browser: | Chrome 124 / Firefox 125
Test Case ID: | TC-S3 |  | Version: | 1.0
Written By: | Project Team |  | Description: | Sprint 3 – Citizen features, activity logging, exposure, admin
Tested By: | Project Team |  | Tested On: | TBD
Test # | Date | Action / Test Step | Expected Results | Actual Results | Pass?
19.0 |  | Citizen views dashboard AQI readings filtered by location | Readings filtered correctly for selected location | Pending | Pending
20.0 |  | Citizen logs outdoor activity (type=Cycling, duration=60 min, location=Hyderabad) | Activity saved; exposure calculated = 60 × AQI | Pending | Pending
21.0 |  | Citizen logs activity with duration=0 | Validation error: 'Duration must be > 0' | Pending | Pending
22.0 |  | Citizen views Exposure History page | Chart showing exposure over time per location | Pending | Pending
23.0 |  | Citizen views personalised health advisory based on exposure | Advisory tailored to citizen's logged exposure | Pending | Pending
24.0 |  | Admin logs in and views user list | All registered users listed with roles | Pending | Pending
25.0 |  | Admin changes a citizen's role to Officer | Role updated; user now has officer permissions | Pending | Pending
26.0 |  | Admin configures advisory threshold for 'Good' category (0–50) | Threshold saved and applied to advisory logic | Pending | Pending
27.0 |  | Admin views system-wide AQI report | Aggregated AQI data shown by location and date | Pending | Pending
28.0 |  | Unauthenticated user accesses /activities/ | 401 Unauthorized returned | Pending | Pending
29.0 |  | Citizen accesses /admin/ panel | 403 Forbidden – access denied | Pending | Pending
30.0 |  | Run full Django test suite (30 existing tests) | All 30 tests pass | Pending | Pending