## sprint-1
Sprint 1 Backlog — Air Quality Monitoring & Health Advisory System
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Officer Login (US-01) | 8 | Backend | Complete | 8 | 8 | 6 | 4 | 2 | 0 | Done – JWT + DRF
Create User Model & JWT auth |  |  | Complete
Login / Register API endpoints |  |  | Complete
Manage Locations (US-02) | 8 | Backend | Complete | 8 | 8 | 6 | 4 | 2 | 0 | Done
Location Model & migration |  |  | Complete
Location CRUD API |  |  | Complete
Manual AQI Entry (US-03) | 8 | Backend | Complete | 8 | 8 | 6 | 4 | 2 | 0 | Done
AQIReading Model & validation |  |  | Complete
POST /aqi-readings/ endpoint |  |  | Complete
Dashboard AQI View (US-04) | 8 | Frontend | Complete | 8 | 8 | 6 | 4 | 2 | 0 | Done
AQI Table component |  |  | Complete
Dashboard page layout |  |  | Complete
Total

## sprint-2
Sprint 2 Backlog — Air Quality Monitoring & Health Advisory System
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
CSV Bulk Upload (US-05) | 13 | Backend/Frontend | Complete | 13 | 13 | 10 | 7 | 4 | 0 | Done
Upload UI in AQIForm |  |  | Complete
POST /upload-csv/ endpoint |  |  | Complete
Parse & validate CSV rows |  |  | Complete
OpenAQ API Integration (US-06) | 13 | Backend | In Progress | 13 | 13 | 10 | 7 | 4 | 0 | API errors remain
POST /fetch-openaq/ endpoint |  |  | Complete
Error handling & retry logic |  |  | In Progress
AQI Trend Chart (US-07) | 13 | Frontend | In Progress | 13 | 13 | 10 | 7 | 4 | 4 | Chart pending polish
Plotly line chart component |  |  | In Progress
Colour-banded AQI zones |  |  | Not Started
Health Advisory Banner (US-08) | 8 | Frontend | Complete | 8 | 8 | 6 | 4 | 2 | 0 | Done
EPA category logic |  |  | Complete
Banner colour + message |  |  | Complete
Citizen Login & Public View (US-09) | 9 | Full-stack | In Progress | 9 | 9 | 7 | 5 | 3 | 2 | Auth done, views pending
Citizen role register/login |  |  | Complete
Role-based UI (officer form hidden) |  |  | Complete
Citizen dashboard – read-only view |  |  | In Progress
Total

## sprint-3
Sprint 3 Backlog — Air Quality Monitoring & Health Advisory System
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Citizen Dashboard – AQI & Filter (US-10,11) | 13 | Full-stack | Not Started | 13
Citizen Dashboard page |  |  | Not Started
Location filter for citizens |  |  | Not Started
AQI chart for citizens |  |  | Not Started
Log Activities Model & API (US-12) | 13 | Backend | Not Started | 13
Activity model (type, duration, location) |  |  | Not Started
POST /activities/ endpoint |  |  | Not Started
Activity log UI for citizens |  |  | Not Started
Exposure History & Calculation (US-13,14) | 16 | Full-stack | Not Started | 16
Exposure = duration × AQI calculation |  |  | Not Started
GET /exposure-history/ endpoint |  |  | Not Started
Personalised advisory from exposure |  |  | Not Started
Exposure History page (charts) |  |  | Not Started
Admin – Manage Users (US-15) | 8 | Full-stack | Not Started | 8
Admin user list & role management |  |  | Not Started
Deactivate / promote users |  |  | Not Started
Admin – Advisory Rules & Reports (US-16,17) | 6 | Full-stack | Not Started | 6
Configure advisory thresholds |  |  | Not Started
View system-wide AQI reports |  |  | Not Started
Total